BatchSphere Operations Cloud

Full-Stack Development Roadmap

Frontend (React + TypeScript)  ·  Backend (Spring Boot + PostgreSQL)  ·  March 2026

| Phases | Total Tasks | Est. Duration | Backend Files | Frontend Files |
| --- | --- | --- | --- | --- |
| 9 Phases | 120+ Tasks | ~34 Weeks | 70+ Java Files | 30+ TSX Files |
| Phases 0-4 harden the existing codebase. Phases 5-9 build the new modules (VQ, QMS, LIMS, HRMS) and production infrastructure. |  |  |  |  |

PHASE 0    Critical Fixes — Do Before Anything Else   ·   2–3 days

These are bugs and structural issues that will become increasingly painful to fix once the codebase grows. Fix them first — no new features until these are done.

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| FIX | Rename package `transcations` → `transactions` across all 30+ Java files | 1 day | Backend | Global refactor; do in IntelliJ: Right-click package → Refactor → Rename |
| FIX | BatchController.deactivateBatch() — add missing `/{id}` in @DeleteMapping | 30 min | Backend | Documented bug in ARCHITECTURE.md |
| FIX | Soft-delete warehouse locations (Warehouse/Room/Rack/Shelf/Pallet) — replace hard DELETE with isActive=false | 2 hrs | Backend | Prevents FK violations when inventory references a location |
| FIX | Add Flyway migration V25: add deleted_at column to all 5 warehouse location tables | 30 min | DB | Supports soft-delete |
| FIX | Validate Pallet.storageCondition == parent Room.storageCondition on create/update | 1 hr | Backend | GMP compliance — already partially done in GrnServiceImpl but not in WarehouseLocationServiceImpl |
| FIX | Remove hardcoded createdBy: 'admin' from all 5 warehouse forms in frontend | 30 min | Frontend | Use currentUser from Zustand appShellStore |
| FIX | Remove hardcoded createdBy: 'admin' from GRN, Sampling, and all other frontend forms | 1 hr | Frontend | Needs auth first — put placeholder for now, wire in Phase 1 |
| FIX | CORS: Lock down allowed origins in WebCorsConfig (remove wildcard for production) | 30 min | Backend | Currently allows all origins |

PHASE 1    Security & Authentication   ·   1.5 weeks

SecurityConfig is currently permitAll() — every endpoint is completely open. This must be addressed before any real data goes in. Build it properly once so every future module is secured automatically.

1.1  Backend — Spring Security + JWT

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| NEW | Add User entity: id, username, email, passwordHash, role (enum), isActive, createdAt | 2 hrs | Backend | Roles: ADMIN, QC_ANALYST, QC_MANAGER, QA, WAREHOUSE_OP, PROCUREMENT |
| NEW | Add V26 Flyway migration: create users table | 30 min | DB |  |
| NEW | Implement UserDetailsService loading User by username | 1 hr | Backend |  |
| NEW | Add JWT utility class: generate, validate, extract claims | 2 hrs | Backend | Use jjwt library — add to pom.xml |
| NEW | Add JwtAuthenticationFilter (OncePerRequestFilter) | 1.5 hrs | Backend | Validates token on every request |
| UPD | Update SecurityConfig: replace permitAll() with role-based rules per endpoint path | 2 hrs | Backend | e.g. /api/grns/** needs WAREHOUSE_OP+, /api/sampling/** needs QC_ANALYST+ |
| NEW | Add AuthController: POST /api/auth/login, POST /api/auth/refresh, POST /api/auth/logout | 2 hrs | Backend | Returns JWT access token + refresh token |
| NEW | Add PasswordEncoder bean (BCryptPasswordEncoder) | 15 min | Backend |  |
| NEW | Add default admin user seed in data.sql or Flyway V27 | 30 min | DB | So system is usable after first run |

1.2  Frontend — Auth Flow

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| NEW | Create LoginPage.tsx: email + password form, calls POST /api/auth/login | 3 hrs | Frontend |  |
| NEW | Create authStore.ts (Zustand): store token, user, role, isAuthenticated | 1 hr | Frontend | Persist to localStorage |
| NEW | Create ProtectedRoute component: redirects to /login if not authenticated | 1 hr | Frontend | Wrap all routes in router.tsx |
| NEW | Add axios/fetch interceptor: attach Bearer token to all API requests | 1 hr | Frontend | Add 401 handler to redirect to login |
| UPD | Update appShellStore currentUser: populate from JWT claims not hardcoded | 30 min | Frontend |  |
| UPD | Update all form createdBy fields: use currentUser.username from authStore | 1 hr | Frontend | Replaces 'admin' placeholder |
| NEW | Role-based UI: hide/disable buttons user's role cannot use (e.g. hide Approve if not QC_MANAGER) | 2 hrs | Frontend |  |

PHASE 2    Backend API Completeness   ·   2 weeks

Several critical workflows exist in the data model but are not yet implemented in the API. These block the frontend from being feature-complete.

2.1  Inventory — Status Transitions & Movements

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| NEW | Add PUT /api/inventory/{id}/status: transition QUARANTINE→SAMPLING→UNDER_TEST→RELEASED/REJECTED/BLOCKED | 3 hrs | Backend | Validate allowed transitions — use a state machine enum |
| NEW | Add POST /api/inventory/adjust: stock adjustment with reason, adjustedBy, adjustedAt | 2 hrs | Backend | Creates an InventoryTransaction of type ADJUSTMENT |
| NEW | Add POST /api/inventory/transfer: move stock between pallet locations | 2 hrs | Backend | Creates TRANSFER transaction; validates storage condition compatibility |
| NEW | Add POST /api/inventory/issue: outbound dispatch — reduces qty, creates OUTBOUND transaction | 2 hrs | Backend | GMP requires dispatch reference (dispatch order no.) |
| NEW | Add V28 Flyway migration: add adjustment_reason, dispatch_ref columns to inventory_transaction | 30 min | DB |  |
| NEW | Add GET /api/inventory/summary: counts by status (for dashboard KPIs) | 1 hr | Backend | Returns {QUARANTINE: n, SAMPLING: n, RELEASED: n, ...} |

2.2  Sampling — Complete the QC Decision Workflow

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| NEW | Add PUT /api/sampling-requests/{id}/complete: mark physical sampling complete, update status → UNDER_TEST | 1.5 hrs | Backend |  |
| UPD | QC Decision endpoint: on APPROVED → call InventoryService to set status RELEASED; on REJECTED → REJECTED | 2 hrs | Backend | Currently QC decision exists but inventory status update is missing |
| NEW | Add sampled quantity reconciliation: track how much was taken from each container | 1.5 hrs | Backend | Reduces container qty by sampled amount |
| NEW | Add GET /api/sampling-requests/summary: counts by status (for dashboard KPI) | 1 hr | Backend |  |

2.3  GRN — Multi-Item & Improvements

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| CHK | Verify GrnService correctly handles multiple GrnItems in one GRN (entity supports it, verify service logic) | 2 hrs | Backend |  |
| NEW | Add PUT /api/grns/{id}/cancel with reason field — update all containers/labels/inventory on cancel | 2 hrs | Backend | Currently cancel exists but downstream effects need to be verified |
| NEW | Add GET /api/grns/summary: counts by status (for dashboard KPI — pending, received, cancelled) | 1 hr | Backend |  |
| NEW | Add GET /api/grns/{id}/labels/print-data: returns all label data for a GRN for PDF/label generation | 1.5 hrs | Backend | Frontend needs this for pallet label printing |

2.4  Warehouse Location — Enhancements

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| NEW | Auto-generate compound locationCode on Pallet create: {WH_CODE}-{ROOM_CODE}-{RACK_CODE}-{SHELF_CODE}-{PALLET_CODE} | 2 hrs | Backend | Store in pallet table; add to V29 migration |
| NEW | Add GET /api/warehouses/{id}/tree: return full hierarchy as nested JSON (for tree view UI) | 2 hrs | Backend | Warehouse with rooms, racks, shelves, pallets nested |
| NEW | Add GET /api/pallets/available?storageCondition=X: pallets with no current inventory for put-away suggestion | 1.5 hrs | Backend |  |

2.5  Cross-Cutting Backend Improvements

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| NEW | Add AOP audit interceptor: log every POST/PUT/DELETE to audit_log table (entity, entityId, action, userId, timestamp, oldValue, newValue) | 4 hrs | Backend | 21 CFR Part 11 requirement — use Spring AOP @Around |
| NEW | Add V30 Flyway migration: create audit_log table | 30 min | DB |  |
| NEW | Add Bean Validation (@Valid, @NotBlank, @NotNull, @Size) to all DTO request classes | 3 hrs | Backend | Currently most DTOs have no validation annotations |
| NEW | Add proper error codes to ErrorResponse: errorCode field (e.g. DUPLICATE_MATERIAL_CODE, INVALID_STATUS_TRANSITION) | 2 hrs | Backend | Frontend can show better error messages |
| NEW | Add @Transactional to all service methods that modify data | 1 hr | Backend | Check GrnServiceImpl — complex orchestration needs rollback safety |
| UPD | Switch all N+1 queries to JOIN FETCH or @EntityGraph where Batch, Material, Pallet are loaded | 2 hrs | Backend | Currently many associations use lazy loading + separate queries |

PHASE 3    Frontend Completeness   ·   2 weeks

Phase 1 work (splitting pages, React Query, Zustand, lazy loading) is largely done. Phase 3 completes the actual feature functionality on the existing modules.

3.1  Dashboard — Wire Live Data

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| UPD | Wire 4 KPI cards to real API: pending GRNs count, quarantine inventory count, sampling queue count, released stock count | 2 hrs | Frontend | Use React Query; call /api/grns/summary, /api/inventory/summary, /api/sampling-requests/summary |
| UPD | Wire Recent Activity feed to real InventoryTransaction data | 2 hrs | Frontend | Call GET /api/inventory/transactions?size=10&sort=createdAt,desc |
| NEW | Add auto-refresh every 60 seconds on Dashboard KPIs (React Query refetchInterval) | 30 min | Frontend |  |

3.2  GRN — Multi-Item & Label Print

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| UPD | Multi-item GRN form: dynamic list of GrnItems (Add Item / Remove Item rows) | 4 hrs | Frontend | Currently only 1 item per GRN form |
| NEW | Pallet label preview modal: show label layout with QR code, batch, material, storage condition | 3 hrs | Frontend | Fetch from /api/grns/{id}/labels/print-data |
| NEW | Print button on GRN detail: @media print CSS to print labels without UI chrome | 2 hrs | Frontend |  |
| UPD | GRN Cancel: confirmation modal with reason field | 1 hr | Frontend |  |

3.3  Inventory — Transitions & Adjustments

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| NEW | Status transition button on inventory row: Release / Reject / Send-to-Test (role-gated) | 3 hrs | Frontend | Calls PUT /api/inventory/{id}/status |
| NEW | Stock adjustment modal: quantity delta + mandatory reason field | 2 hrs | Frontend |  |
| NEW | Stock transfer modal: select destination pallet (filtered by compatible storage condition) | 2 hrs | Frontend |  |
| UPD | Inventory table: add column sorting, filter by status, filter by material | 2 hrs | Frontend |  |

3.4  Sampling — Complete Workflow

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| NEW | 'Mark Sampling Complete' button on sampling plan: calls PUT /api/sampling-requests/{id}/complete | 1 hr | Frontend |  |
| UPD | QC Decision: on Approve confirm → show that inventory will be RELEASED; on Reject confirm → show it will be REJECTED | 1.5 hrs | Frontend | User needs to understand the downstream impact |
| NEW | Sampling queue: add filter by status (PENDING / IN_PROGRESS / COMPLETED) | 1 hr | Frontend |  |

3.5  Master Data — Warehouse Tree View

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| NEW | Add collapsible tree view of warehouse hierarchy (WH → Room → Rack → Shelf → Pallet) using /api/warehouses/{id}/tree | 4 hrs | Frontend | Much better UX than flat tabs; show location codes |
| UPD | Show compound locationCode on each pallet card/row once auto-generation is in Phase 2 | 30 min | Frontend |  |
| NEW | Add isActive toggle (deactivate/reactivate) for warehouse locations instead of delete | 1.5 hrs | Frontend | Pairs with Phase 0 soft-delete backend change |

PHASE 4    Performance Hardening   ·   1 week

The system will be slow under real pharmaceutical data volumes without proper indexing, query optimization, and caching. Address this before adding new modules.

4.1  Database Indexing

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| NEW | Add V31 migration: indexes on grn.status, grn.receipt_date, grn.supplier_id, grn.vendor_id | 30 min | DB | Most common GRN query patterns |
| NEW | Add V31 migration: indexes on inventory.material_id, inventory.batch_id, inventory.pallet_id, inventory.status | 30 min | DB |  |
| NEW | Add V31 migration: indexes on sampling_request.grn_id, sampling_request.status | 30 min | DB |  |
| NEW | Add V31 migration: indexes on batch.material_id, batch.status | 30 min | DB |  |
| NEW | Add V31 migration: composite index on inventory (material_id, batch_id, pallet_id) — the most common lookup | 20 min | DB |  |

4.2  Backend Query Optimization

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| UPD | Fix N+1 in GrnServiceImpl.getGrns(): add JOIN FETCH for supplier, vendor, VBU | 2 hrs | Backend | Currently each GRN row triggers 3 extra queries |
| UPD | Fix N+1 in InventoryController: add JOIN FETCH for material and batch | 1.5 hrs | Backend |  |
| NEW | Add Spring Cache (@Cacheable) to material, warehouse, spec, moa, sampling-tool lists (master data rarely changes) | 2 hrs | Backend | Use in-memory Caffeine cache — no Redis needed yet |
| NEW | Add cache eviction (@CacheEvict) on all master data create/update/delete operations | 1 hr | Backend |  |
| UPD | Review GrnServiceImpl.receiveGrn() — currently runs multiple separate INSERTs; wrap in single transaction, batch-insert containers and labels | 3 hrs | Backend | Use saveAll() for containers and labels |
| NEW | Add spring.jpa.properties.hibernate.jdbc.batch_size=50 to application.yaml | 10 min | Backend | Enables JDBC batch inserts |

4.3  Frontend Performance

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| CHK | Verify all routes are lazy-loaded (router.tsx looks correct — confirm bundle sizes with vite build --report) | 1 hr | Frontend |  |
| NEW | Add staleTime per query type: master data (10 min), transactions (30 sec), dashboard KPIs (1 min) | 1 hr | Frontend | Currently queryClient.ts has one global 30s staleTime |
| UPD | GRN list: ensure pagination is working (15 per page already coded — verify total page count is displayed) | 30 min | Frontend |  |
| NEW | Add virtual scroll (or pagination) for Inventory table — will have 1000s of rows in production | 2 hrs | Frontend |  |
| UPD | Replace all inline color strings in JSX with Tailwind classes (avoids style recalculations) | 2 hrs | Frontend |  |

PHASE 5    Vendor Qualifications Module   ·   2.5 weeks

This is the highest-priority new module — it directly gates GRN CoA-based release. A vendor must have an active qualification for a material before CoA-based release is permitted.

5.1  Backend

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| NEW | Create package: com.batchsphere.core.vendorqualification | 30 min | Backend |  |
| NEW | Entity: VendorQualification — id, vendorId, materialId, status (APPROVED/PROVISIONAL/SUSPENDED/REVOKED), approvedDate, expiryDate, qualificationRef, approvedBy | 2 hrs | Backend |  |
| NEW | Entity: QualificationDocument — id, qualificationId, docType (GMP_CERT/COA_TEMPLATE/AUDIT_REPORT), fileName, filePath, expiryDate | 1.5 hrs | Backend |  |
| NEW | Entity: VendorAudit — id, vendorId, auditDate, auditType (INITIAL/PERIODIC/FOR_CAUSE), outcome, score, auditorId | 1.5 hrs | Backend |  |
| NEW | Entity: AuditFinding — id, auditId, findingType (CRITICAL/MAJOR/MINOR), description, capaRef, closedDate | 1 hr | Backend |  |
| NEW | V32 Flyway migration: create all 4 vendor qualification tables | 1 hr | DB |  |
| NEW | VendorQualificationService: CRUD + approve/suspend/revoke workflow methods | 3 hrs | Backend |  |
| NEW | VendorQualificationController: REST endpoints for all operations | 2 hrs | Backend |  |
| NEW | Add isVendorQualifiedForMaterial(vendorId, materialId) helper — used by GrnService to validate CoA-based release eligibility | 1 hr | Backend |  |
| UPD | GrnServiceImpl: call isVendorQualifiedForMaterial() when sampling method is COA_BASED_RELEASE — reject if not qualified | 1.5 hrs | Backend | GMP requirement |
| NEW | VQ document upload endpoint: multipart upload for GMP certs, CoA templates, audit reports | 1.5 hrs | Backend | Reuse LocalStorageService pattern |
| NEW | GET /api/vendor-qualifications/expiring?days=60: returns qualifications expiring in next 60 days (for dashboard widget) | 1 hr | Backend |  |

5.2  Frontend

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| NEW | Create features/vendor-qualifications/VendorQualificationsPage.tsx | 1 hr | Frontend | Skeleton + route in router.tsx |
| NEW | Qualification list table: vendor, material, status badge, approved date, expiry date, days-to-expiry warning | 3 hrs | Frontend |  |
| NEW | Create/Edit qualification form: vendor dropdown, material dropdown, status, dates, approver | 2 hrs | Frontend |  |
| NEW | Document upload section: per qualification, upload GMP cert / CoA template / audit report | 2 hrs | Frontend |  |
| NEW | Audit records sub-section: list audits for selected vendor, create new audit record | 2 hrs | Frontend |  |
| NEW | Expiry warning cards on Dashboard: show vendors with qualification expiring in 30/60/90 days | 1.5 hrs | Frontend |  |
| UPD | Sampling page: show VQ status badge next to vendor name — APPROVED (green), PROVISIONAL (amber), SUSPENDED (red) | 1 hr | Frontend |  |

PHASE 6    QMS — Quality Management System   ·   5 weeks

Deviations, CAPAs, Change Controls, and SOP management. The regulatory backbone of the platform.

6.1  Deviation Management

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| NEW | Entity: Deviation — deviationNo (auto), area, type, severity, description, detectedDate, detectedBy, batchRef, grnRef, status (OPEN/INVESTIGATING/PENDING_CAPA/CLOSED) | 3 hrs | Backend |  |
| NEW | Entity: DeviationInvestigation — deviationId, rootCause, contributingFactors, productImpact, disposition | 1.5 hrs | Backend |  |
| NEW | V33 migration: create deviation tables; deviation sequence for deviationNo generation | 1 hr | DB |  |
| NEW | DeviationService: CRUD + status workflow + link to CAPA | 2 hrs | Backend |  |
| NEW | Frontend: DeviationsPage with queue, create form, investigation section, close workflow | 5 hrs | Frontend |  |

6.2  CAPA Management

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| NEW | Entity: Capa — capaNo (auto), source (DEVIATION/AUDIT/OOS/COMPLAINT), sourceRef, type (CORRECTIVE/PREVENTIVE), description, assigneeId, dueDate, status | 2 hrs | Backend |  |
| NEW | Entity: CapaEvidence — capaId, description, evidenceFile, uploadedBy, uploadedAt | 1 hr | Backend |  |
| NEW | Entity: CapaEffectivenessCheck — capaId, checkDueDate, outcome (EFFECTIVE/INEFFECTIVE/PENDING), checkedBy | 1 hr | Backend |  |
| NEW | V34 migration: create CAPA tables | 45 min | DB |  |
| NEW | CapaService: CRUD + close workflow + effectiveness check | 2 hrs | Backend |  |
| NEW | Frontend: CapaPage with list, create form, evidence upload, effectiveness section | 5 hrs | Frontend |  |
| UPD | Deviation → CAPA link: 'Create CAPA from Deviation' button that pre-populates CAPA fields | 1.5 hrs | Frontend |  |

6.3  Change Control

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| NEW | Entity: ChangeControl — changeNo, category (PROCESS/MATERIAL/EQUIPMENT/SOP), description, justification, riskLevel, regulatoryImpact, implementationDate, status | 2 hrs | Backend |  |
| NEW | V35 migration: create change_control table | 30 min | DB |  |
| NEW | Frontend: ChangeControlPage | 4 hrs | Frontend |  |

6.4  SOP / Document Register

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| NEW | Entity: SopDocument — docNo, title, version, status (DRAFT/REVIEW/APPROVED/SUPERSEDED), effectiveDate, reviewDate, owner, approver | 2 hrs | Backend |  |
| NEW | Entity: SopReadReceipt — sopId, userId, acknowledgedAt | 1 hr | Backend |  |
| NEW | V36 migration: create sop tables | 30 min | DB |  |
| NEW | Frontend: SopRegisterPage with version history, upload, review workflow, acknowledgement tracking | 5 hrs | Frontend |  |

6.5  E-Signature Framework

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| NEW | Entity: ElectronicSignature — entityType, entityId, meaningText, userId, timestamp, ipAddress, signatureHash | 2 hrs | Backend |  |
| NEW | ESignatureService: re-authenticate user, record signature, attach to entity | 2 hrs | Backend | 21 CFR Part 11 compliance |
| NEW | Frontend: ESignatureModal component — meaning text + password re-entry dialog | 2 hrs | Frontend | Reusable across GRN, QC Decision, Deviation close, CoA approve |
| NEW | V37 migration: create electronic_signature table | 30 min | DB |  |

PHASE 7    LIMS — Laboratory Information Management   ·   6 weeks

The most complex new module. Manages test work orders, result entry, OOS investigations, instrument qualification, and Certificate of Analysis generation.

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| NEW | Entity: WorkOrder — woNo (auto), samplingRequestId, batchId, assignedAnalyst, status (PENDING/IN_PROGRESS/COMPLETED), requiredByDate | 2 hrs | Backend |  |
| NEW | Entity: TestRequest — woId, testCode, specId, moaId, instrumentId, methodVersion | 1.5 hrs | Backend |  |
| NEW | Entity: TestResult — testRequestId, parameterName, unit, resultValue, lowerLimit, upperLimit, passStatus (PASS/FAIL/OOS), enteredBy, reviewedBy | 2 hrs | Backend |  |
| NEW | Entity: OosInvestigation — testResultId, phase (PHASE1_LAB/PHASE2_FULL), rootCause, disposition, approvedBy | 1.5 hrs | Backend |  |
| NEW | Entity: Instrument — instrNo, name, type, location, calibrationDue, qualStatus | 1.5 hrs | Backend |  |
| NEW | Entity: CalibrationRecord — instrumentId, type, performedBy, performedAt, passStatus, nextDueDate | 1 hr | Backend |  |
| NEW | Entity: CoA — batchId, woId, coaNo, status (DRAFT/APPROVED/ISSUED), approvedBy, issuedAt | 1.5 hrs | Backend |  |
| NEW | V38 migration: create all LIMS tables | 1.5 hrs | DB |  |
| NEW | WorkOrderService: auto-create work orders when sampling plan is approved; assign to analyst | 2 hrs | Backend |  |
| NEW | TestResultService: result entry with auto pass/fail evaluation against spec limits; flag OOS immediately | 3 hrs | Backend |  |
| NEW | OosService: Phase 1 lab error investigation; Phase 2 full investigation workflow | 3 hrs | Backend |  |
| NEW | CoaService: auto-generate CoA from approved results; PDF export using iText or Apache FOP | 4 hrs | Backend |  |
| NEW | Frontend: WorkOrderQueuePage, ResultEntryPage, OosInvestigationPage, InstrumentRegisterPage, CoaPage | 20 hrs | Frontend | Large module — ~5 separate pages |
| NEW | Frontend: Trend analysis chart per parameter (Recharts LineChart) | 3 hrs | Frontend | Results over time per material/batch |

PHASE 8    HRMS — Human Resource Management   ·   3.5 weeks

GMP requires documented evidence that personnel performing regulated tasks are trained and competent. HRMS provides that evidence and integrates with access control.

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| NEW | Entity: Employee — empNo, name, department, role, site, status, hireDate, reportingManager, linkedUserId | 2 hrs | Backend |  |
| NEW | Entity: Qualification — empId, type (EDUCATION/PROFESSIONAL_CERT/INTERNAL_CERT), name, issuedBy, issueDate, expiryDate | 1.5 hrs | Backend |  |
| NEW | Entity: TrainingRecord — empId, type (SOP_READ/GMP_REFRESHER/EQUIPMENT/JOB_SPECIFIC), title, completedDate, score, passStatus, validity (months) | 1.5 hrs | Backend |  |
| NEW | Entity: Competency — empId, taskCode, authorisedFor, assessedDate, nextReviewDate | 1 hr | Backend |  |
| NEW | V39 migration: create HRMS tables | 1 hr | DB |  |
| NEW | TrainingService: track completion, validate expiry, check compliance per role | 2 hrs | Backend |  |
| NEW | CompetencyService: isAuthorisedFor(empId, taskCode) — used to gate e-signatures in QMS/LIMS | 1.5 hrs | Backend |  |
| NEW | GET /api/hrms/training-matrix: compliance % per department and SOP (for dashboard) | 2 hrs | Backend |  |
| NEW | GET /api/hrms/expiring-training?days=30: list of employees with training expiring soon | 1 hr | Backend |  |
| NEW | Frontend: EmployeeRegisterPage, TrainingRecordsPage, CompetencyPage, TrainingMatrixDashboard | 12 hrs | Frontend |  |

PHASE 9    Infrastructure & DevOps   ·   Ongoing

Build the deployment, monitoring, and testing infrastructure alongside feature work. Don't leave this until the end.

9.1  Testing

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| NEW | Backend unit tests: service layer tests with Mockito for GrnService, InventoryService, SamplingService | 1 week | Backend | H2 in-memory DB is already configured for tests |
| NEW | Backend integration tests: @SpringBootTest for full GRN receipt flow (end-to-end) | 3 days | Backend |  |
| NEW | Frontend unit tests: Vitest + React Testing Library for form validation and status badge rendering | 3 days | Frontend |  |
| NEW | Frontend E2E tests: Playwright for critical flows (GRN create → receive → sampling → QC approve) | 1 week | Frontend |  |

9.2  Docker & Deployment

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| NEW | Add Dockerfile for Spring Boot backend (multi-stage build with Eclipse Temurin 17) | 2 hrs | DevOps |  |
| NEW | Add Dockerfile for React frontend (nginx serving dist/) | 1 hr | DevOps |  |
| NEW | Add docker-compose.yml: postgres + backend + frontend + (optional) redis | 2 hrs | DevOps | One command to run the full stack locally |
| NEW | Add application-prod.yaml: production database URL from env vars, no show_sql, proper CORS origin | 1 hr | DevOps | Never commit real credentials |
| NEW | Add .env.example with required environment variables documented | 30 min | DevOps |  |

9.3  Monitoring & Observability

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| NEW | Add spring-boot-actuator: health, info, metrics endpoints | 30 min | Backend | Already in Spring Boot starter — just enable in application.yaml |
| NEW | Add Micrometer + Prometheus metrics export | 1 hr | Backend |  |
| NEW | Add structured JSON logging (Logback with logstash-logback-encoder) | 1 hr | Backend | Parseable logs for production monitoring |
| NEW | Add request/response logging filter: log method, path, statusCode, durationMs for all API calls | 1 hr | Backend |  |

9.4  CI/CD Pipeline

| Tag | Task | Effort | Layer | Notes |
| --- | --- | --- | --- | --- |
| NEW | Add GitHub Actions workflow: on PR → run mvn test, npm test, build frontend | 2 hrs | DevOps |  |
| NEW | Add GitHub Actions workflow: on merge to main → build Docker images, push to registry | 2 hrs | DevOps |  |
| NEW | Add automated DB backup script (pg_dump) with cron — daily backup to S3 or local | 1 hr | DevOps |  |

MASTER TIMELINE OVERVIEW

| Phase | Name | Duration | Covers | Cumulative |
| --- | --- | --- | --- | --- |
| 0 | Critical Fixes | 2–3 days | Fix package typo, soft-delete, Pallet validation, CORS | ~3 days |
| 1 | Security & Auth | 1.5 weeks | JWT, RBAC, LoginPage, protected routes, user context | ~2 weeks |
| 2 | Backend API Completeness | 2 weeks | Inventory transitions, audit log, Bean Validation, N+1 fixes | ~4 weeks |
| 3 | Frontend Completeness | 2 weeks | Multi-item GRN, label print, inventory transitions, live KPIs | ~6 weeks |
| 4 | Performance Hardening | 1 week | DB indexes, caching, batch inserts, lazy loading review | ~7 weeks |
| 5 | Vendor Qualifications | 2.5 weeks | Full VQ module: entities, API, workflow, frontend pages | ~10 weeks |
| 6 | QMS | 5 weeks | Deviation, CAPA, Change Control, SOP register, e-signature | ~15 weeks |
| 7 | LIMS | 6 weeks | Work orders, test results, OOS, instruments, CoA | ~21 weeks |
| 8 | HRMS | 3.5 weeks | Employees, training, competency, training matrix | ~25 weeks |
| 9 | Infrastructure & DevOps | Ongoing | Docker, CI/CD, monitoring, testing, backup | ~34 weeks |

Durations assume one developer working full time. Phases 0–4 should be completed before starting any new module (Phases 5–8). Infrastructure (Phase 9) tasks should be done in parallel with feature phases, not deferred to the end.

Generated by Claude after full review of BatchSphere frontend (React/TypeScript) and backend (Spring Boot/PostgreSQL). All tasks are based on actual code analysis of the live repository.